Meeting Minutes

9 February 2026

Online meeting 4:00-4:30 PM EAT

Meeting Summary

The participants discussed the potential for mapping disease prevalence in Uganda through literature review and data collection, with an emphasis on creating a publicly accessible resource (website/app). The project aims to identify knowledge gaps across districts, inform research and grant applications, and involve students in research activities. The conversation highlighted the importance of low-cost, scalable methods and leveraging existing data to build a robust research and policy foundation.

Present

- Dr. Abimereki Muzaale

- Prof. Robert Basaza

- Emmanuel Otieno (Secretary)

Absent with Apology

Associate Prof. Elizabeth Kizito

Agenda

1. Discussion of clinical research background and potential for public health mapping.

2. Proposal to map disease prevalence using literature review and existing data.

3. Planning the development of a website/app for data sharing and transparency.

4. Involving students in research activities and publications.

5. Strategies for grant writing and research funding.

6. Clarification of resources and timeline for project implementation.

Decisions

- The team will proceed with a literature-based mapping of disease prevalence across districts in Uganda, beginning with a focus on conditions like depression and other priority diseases.

- A website or app will be developed to publicly display the maps, data gaps, and ongoing research progress.

- The project will serve as a pilot to demonstrate capacity and generate preliminary data to support grant applications.

- Involvement of students in research activities will be prioritized to build capacity and foster academic growth.

- The project will leverage low-cost methods and existing literature to minimize resource requirements.

Next Steps

- Draft a proposal for the mapping project with provisional titles  "Land Scape Mapping of Disease Prevalence in Uganda".

- -Dr Muzaale is going to be the lead PI and lead the writing. He is going to sketch the project outline, timelines for completion of this proposal and the Uganda team write our part.

- Dr Muzalle shall send us literature on Mapping of Disease Prevalences

- The team shall assign roles for literature review and data collection with the aim of identifying districts with no existing studies.

- Begin development of the website/app to host the maps and data.

- Prepare initial grant applications, emphasizing preliminary work and low resource needs.

- Engage students in data analysis and publication efforts.

- Schedule follow-up meeting to review progress and refine project scope when an indicate text on item 2 is available.